## Improvement Plan
CSP Grant Community School Sponsor Quality Improvement Action Plan
Sponsor: | Fordham |  | Submission Date:
Plan Line Number | Performance Measure/ Standard | 2018-2019 3-Point Requirement | Improvement Goal | Strategy | Action | Person(s) Responsible | Estimated Date of Completion | Documentation / Evidence of Completion | Progress Report
Number plan lines consecutively | Enter the name of the Quality Practices Standard with Item Number | Enter the applicable exemplary standard from the Quality Practices rubric | Enter the sponsor's improvement goal for the listed performance measure or standard | Enter the Strategy the sponsor will take to meet the stated Improvement Goal | Enter the Action the sponsor will take to meet the stated Improvement Goal | Enter the name and/or role of the person(s) responsible for meeting the stated improvement goal, strategy and action steps | Enter the estimated date on which the stated improvement goal will be met | Describe the documentation that will be used as evidence of completion of the stated improvement goal or individual action(s) | Describe the progress made toward meeting the stated improvement goal, as of March 30, 2019
1 | D.02 | 2-Point Requirements –and– The sponsor submitted at least six examples of financial review results and six examples of enrollment review results for each selected school –and– The sponsor submitted detailed policies and processes for conducting enrollment and financial reviews. | Meet the standards for the "3 point" requirement | Continue with monthly enrollment and financial reviews, and providing governing boards with as much relevant information as to the financial health of the schools, including follow-up to previously-identified issues brought up by sponsor during the monthly sponsor-treasurer calls and the subsequent sponsor reports to the school governing boards. | Sponsor has rolled out an even more transparent format for reporting monthly enrollment and financial reviews, beginning with the September 2019 sponsor-treasurer meetings. This new format will make it easier for all readers and board members alike, to follow discussions and issues of concern that are raised in any particular month, into subsequent month/s in showing that the sponsor made proactive recommendations to the school’s governing authority, in helping the governing board take action. In short, this new format will be more transparent in showing the sponsor's work and reports with enrollment and financials that meets the standards of "4-points" in D.02 of the Quality Practices Rubric. | Miles Caunin | 1/9/2020 | Please see attachments and documments reference in the CAP Summary Sheet. | In progress.