Sample Literacy Action Plan

Taking Action Goal Statement:  All students will learn and routinely use reading and writing support strategies to enhance literacy and learning in across all content areas.

| A Action Step | B Timeline (target date) | C Lead Person(s) | D Resources Needed | E Specifics of Implementation | F Evidence of Success |
| --- | --- | --- | --- | --- | --- |
| The literacy team will select a common set of literacy support strategies and decide which departments or teams will be responsible for teaching the strategies. | June-July | Literacy team members with input from entire faculty | - Time to meet and consider strategies. - Common Reading Comprehension Strategy Selection Tool | After reviewing student data and seeing where students need additional support, the literacy team will discuss several strategies. The literacy team members will select 3-6 strategies that address these needs. Input will be solicited from teachers to see if others should be added. The literacy team will agree on a common set that teachers will learn and then model for students. Students will be expected to use these strategies routinely across the content areas. | List of strategies selected. |
| All teachers will participate in at least two professional development sessions to learn a common set of strategies. | September-October | - Literacy coach - Teachers - Assistant principal | - Time and stipends for professional development - Handouts, chart paper, etc. for presentations | Literacy coach and selected teachers will work together to present the common strategies to the faculty and invite participation and discussion about the purpose of the strategy and how the strategy can be applied to different content areas. | - Positive professional development evaluations - Teachers awarded inservice credit - Attendance sheets |
| Each department or team will discuss the literacy demands of their content areas and use the common strategies in their instruction. | October- December | Department chairs or team leaders will lead discussions Literacy coach | Meeting time | Each department or team will meet three times. Meeting 1: Discuss the literacy demands of the content area Meeting 2:Plan for the teaching of assigned strategies Meeting 3: Discuss the use of the selected common strategies and make plans for implementation using the gradual release model of responsibility (teach, model, guide practice, independent practice, transfer). Meeting 4: Discuss how lessons went and how to improve on delivery. | - List of strategies to be stressed in each department and frequency of use - Minutes of meetings |
| All teachers will have multiple opportunities to visit demonstration classrooms, engage in peer coaching, and/or work with a literacy coach to see strategies in action. | January- Feb | Literacy coach Peer coaches | - Schedule for presentations - Sub money to release teachers - Protocol for peer coaching - Observation sheets for demonstration lessons | Literacy coach will select teachers to conduct demonstration lessons. - a schedule will be set for demonstration lessons or peer coaching - teachers will observe lessons - literacy coach and teachers will debrief the lesson. | - Teacher reflections on the lesson. - Demonstration classroom calendars - Peer coaching documentation |
| All teachers will model and teach students the agreed upon literacy support strategies multiple times to strengthen content literacy and learning. | January-April | Assistant principal Literacy Team | Walk-through form that focuses on literacy | - The AP will walk through classrooms three times collecting data on strategy use. - The AP will report findings to the Literacy Team and the entire faculty. - The Literacy Team will discuss ways to raise, improve, or sustain literacy use in content area classrooms. | - Walkthrough data collected monthly reflecting at least 75% of teachers using one or more of the selected strategies. - Evidence of student work incorporating the strategies |
| All students will be able to explain the schoolwide strategies | January-February | Literacy coach Principal | Time for randomly questioning students Focus group questions | - The literacy coach and the principal will stop 2-5 students daily and ask them to explain literacy strategies - The literacy coach will conduct focus groups with students to determine student strategy knowledge and use | Results of focus groups |
| All students will routinely use schoolwide strategies across the curriculum | January-June | Literacy coach Literacy team members | Walk-through form focused on strategy use | - The literacy team will design a walk-through form targeting strategy use by students - The literacy team will conduct walkthroughs monthly, rotating team members | - Walkthrough data - Evidence of student work incorporating the strategies |
| All teachers will share and support one another in strategy use during department and/or team meetings. | March - May | Department chairs or team leaders Literacy coach | Time for meetings | Departments or teams will meet two times to share strategy use and discuss ways to improve or sustain use in their content area. Meeting 1: Share strategy use. Meeting 2: Make a common agreement about when and how strategies will be used throughout the department or team for the next school year and how to train new teachers and new students in strategy use. | Teacher reflections Strategy use plan Common agreement about strategy use |